90-Day Authority Building Plan

Project: TradifyApp Social Authority & Content Growth
Primary Goal: Position TradifyApp as a trusted trading discipline platform and build authority-driven audience growth using structured short-form content.

Milestone 1 – Strategy, Positioning & Foundation

Timeline: Week 1 – Week 3 (Days 1–21)

Goal: Build the strategic foundation required for long-term authority building before scaling content.

Key Activities

• Positioning Audit

- Analyze TradifyApp messaging

- Review competitor narratives in trading SaaS

- Identify differentiation opportunities

• Audience & Market Analysis

- Define trader segments (retail traders, prop traders, psychology-focused traders)

- Identify common behavioral and discipline gaps

• Content Pillars Development
Define 3–4 core authority pillars:

- Trader Discipline

- Decision Frameworks

- Execution Psychology

- Trade Review Systems

• Authority Voice Development

- Define tone focused on data-driven discipline

- Avoid hype or “get rich trading” messaging

• Profile Optimization

- Bio optimization

- Highlights structure

- Page positioning to present TradifyApp as a trading decision system

• Visual Content System

- Create reusable templates for:

- Reels

- Carousel education posts

- Quick insight snippets

Deliverables

• Positioning Audit Document
• Audience & Competitor Insights
• Defined Content Pillars
• Brand Voice & Messaging Guide
• Optimized Social Profiles
• Content Template Kit

Outcomes

• Clear authority positioning
• Structured content system ready for scale
• Professional brand presence

Milestone 2 – Authority Content System Launch

Timeline: Week 4 – Week 8 (Days 22–60)

Goal: Launch the content engine to start building authority and audience engagement.

Key Activities

• Short-Form Content Strategy

- Develop Reels-first hook framework

- Structure content for trader curiosity and retention

• Content Production System
Weekly structure:

- 3–4 Reels

- 1–2 Carousel educational posts

- 1 insight post or short breakdown

• Series Development
Launch “Trade Breakdown Series”

Format:
Bad Trade → What Went Wrong → Discipline Framework → Correct Execution

Purpose:
Position TradifyApp as a decision-quality platform rather than just a tool.

• Authority Narrative Building
Address common trader problems:

- Emotional trading

- Poor trade journaling

- Lack of decision review frameworks

Deliverables

• 16–20 Reels
• 8–10 Carousel posts
• 4–6 Educational breakdown posts
• Series framework for repeatable authority content

Outcomes

• Stronger audience engagement
• Clear authority narrative
• Consistent publishing system

Milestone 3 – Authority Scaling & Growth Optimization

Timeline: Week 9 – Week 12 (Days 61–90)

Goal: Optimize content performance and strengthen TradifyApp’s thought leadership positioning.

Key Activities

• Performance Analysis

- Analyze engagement data

- Identify top-performing hooks & formats

• Content Optimization

- Double down on winning content themes

- Improve hook structures

• Authority Expansion

- Advanced educational Reels

- Deep trader psychology insights

- Framework-driven posts

• Community Engagement Strategy

- Comment engagement

- Strategic replies to trader questions

- Thought leadership positioning

Deliverables

• Performance Insights Report
• Optimized Content Framework
• 12–15 additional authority posts
• Growth optimization recommendations

Outcomes

• Improved content performance
• Growing authority within trading niche
• Scalable content engine